## Sheet1
milestone | deliverable | start_date | due_date | status | quarter
Draft Feasibility Study | Feasibility Study | 2022-01-12 | 2022-02-07 | complete | Q1
Final Feasibility Study | Feasibility Study | 2022-02-12 | 2022-03-11 | in progress | Q1
Draft Design Drawings | Design Drawings | 2022-01-24 | 2022-03-18 | in progress | Q1
Final Design Drawings | Design Drawings | 2022-04-12 | 2022-05-20 | not started | Q2
Draft Technical Documentation | Technical Documentation | 2022-03-01 | 2022-03-18 | not started | Q1
Final Technical Documentation | Technical Documentation | 2022-03-28 | 2022-04-22 | not started | Q2
Stakeholder Presentation | Presentation |  | 2022-03-25 | not started | Q1
Draft Web Application | Web Application | 2022-02-18 | 2022-03-16 | not started | Q1
Final Web Application | Web Application | 2022-03-28 | 2022-05-27 | not started | Q2
Client Presentation | Presentation |  | 2022-06-03 | not started | Q2